## TANNER Use Cases & Features
Use Cases | Features | Description | Release | Dependencies | Integrations | Cross-Feature Impact | Screens | Tables/Ints | T-Shirt | Eng Weeks
1. Audience Management | 1.1 CSV Upload & Ingestion | • Users upload .csv of domains; system validates (format, duplicates) and stores in S3. Max 10K records/file; <30s processing. • Error log/management for failed imports **Discussion Point: Account name matching to domain (might require fuzzy matching, might not be MVP). Also, Domain + Country (CNN US vs UK, etc). AI potential | MVP | AWS S3 | AWS S3 | 1.2, 1.3, 1.5, 2.2 | #VALUE! | #VALUE! | S | 1
1. Audience Management | 1.2 Audience Builder | • AND/OR logic tree to segment data from CSV + Bombora fields (e.g., intent data). • Supports TTD-compatible JSON output. *Status/Change Log w/ revert back to previous audience, etc. Ability to view historical audience builds. | MVP | 1.1, 1.3, Bombora, TTD | Bombora, TTD | 1.5, 2.2 | #VALUE! | #VALUE! | L | 4
1. Audience Management | 1.3 Audience Field-Mapping Service | • Ingests and normalizes Bombora S3 files (20–60M records/day) using predefined schema mappings (e.g., Bombora’s "company_name" → P360’s "account_name"). • Normalize fields (e.g., company_name, intent_data) for segmentation. Validates data against P360’s taxonomy (e.g., industry verticals, revenue tiers) • Real-time ingestion with validation. • Performance target: Vendor data processing within 4 hours. log mismatches for manual review. | MVP | 1.1, 4.4, AWS S3, Bombora | AWS S3, Bombora, Integrate | 1.2 | #VALUE! | #VALUE! | M | 2
1. Audience Management | 1.4 Audience Deduplication | • Auto-flag duplicate audiences/invalid domains. Invalid Domains = Format (future: company doesn't exist, but out of scope) | MVP | 1.2 |  | 1.5 | #VALUE! | #VALUE! | S | 1
1. Audience Management | 1.5 Audience Export to TTD | • Set-up TTD audience export service using the combined identifier provided by TTD, with batching and API submission • Enrich payloads with first-party cookies (if available) and TTD field mappings (e.g., "P360_audience_id" → "ttd_segment_id"). • Implement retry logic for API failures (max 3 attempts) with exponential backoff. - When does an audience get updated? An audience in tradedesk gets updated upon save in audience builder, full weekly saturation / update from bombora on saturdays. Create tradedesk audience for every audience that's configured in P360. | MVP | 1.2, 6.1, TTD | TTD, AWS S3 | 2.4 | #VALUE! | #VALUE! | S | 1
1. Audience Management | 1.6 ICP Type for Audience Builder | A templatized verison / flag of Audience Builder that allows for A user to signify that this Audience represents their ICP. User has a clear distinction in the UI. The ICP Version of Audience Builder will be used to populate seeds in their TTD Advertiser. | MVP | 1.2, 6.1, TTD | TTD, AWS S3 |  | 0
1. Audience Management | 1.7 Seed Creation - Advertiser | Creation of a Seed in TTD using the populated TDID's that are driven from the selection of the ICP Audience Builder - minimum 10K ID's. | MVP | 1.2, 6.1, TTD | TTD, AWS S3 |  | 0
2. Campaign Orchestration | 2.1 Program Hierarchy | • UI to nest Programs > Campaigns > Line Items. • DB schema supports parent-child relationships. - At some point, programs will need to hold files (non-mvp, but nice-to-have) - Program --> IO, Campaign --> Line Item | MVP |  |  | 2.2, 2.3 | #VALUE! | #VALUE! | M | 2
2. Campaign Orchestration | 2.2 Campaign Configuration | • Set budget, flight dates, KPIs, and assign audiences (from 1.2). • Real-time validation (e.g., budget ≤ Program cap). Status / creation based off status, errors for Uis | MVP | 1.2, 2.1 |  | 2.4, 2.5 | #VALUE! | #VALUE! | S | 1
2. Campaign Orchestration | 2.3 Line Item Configuration | • Configure bids, creatives, pacing. • Validate against TTD constraints (e.g., MaxBidCPM). - Line item configs are optional (nullable, etc) | MVP | 2.2, TTD | TTD | 2.4 | #VALUE! | #VALUE! | S | 1
2. Campaign Orchestration | 2.4 Campaign Sync to TTD | • Call TTD APIs (/v3/campaign, /v3/adgroup). • Retry logic for API failures. • Log sync status. • Performance target: <5 seconds response for campaign actions. | MVP | 2.2, 2.3, TTD | TTD, 4.7 | 1.5 | #VALUE! | #VALUE! | S | 1
2. Campaign Orchestration | 2.5 Seed Creation from Audience Builder | Construct a Seed associated with the campaign based on the audience matching within the Pipeline360 product - minimum 10K cookies. | MVP | 1.2, 1.4, 1.6, 1.7, 1.8
2. Campaign Orchestration | 2.5 Forecast Generation Engine | • Allows users (internal or buyer) to generate media delivery forecasts by combining TTD reach estimates with audience inputs (size, duration, geography, industry vertical) • Accepts inputs such as audience size, duration, geography, industry vertical, etc. • Returns estimated reach, impressions, match rate, and delivery window (confidence interval ±10%). • Can be run pre-campaign, post-audience creation • Should support multiple forecast versions per campaign • Stores forecasts in Program/Campaign records with versioning (max 5 versions per campaign). • Required as part of buyer-facing media plan review workflow • Performance target: <3s response time for forecasts with audiences <100K domains. • Validates inputs against TTD constraints (e.g., min/max budget, geo availability). | Post-MVP | 1.2, TTD, 2.2 | TTD |  | #VALUE! | #VALUE! | L | 4
2. Campaign Orchestration | 2.6 Campaign Metadata Enrichment | • Add optional metadata fields to campaigns: • Campaign Type (Display, Syndication, Marketplace) • Read/Write state based on role (Campaign Manager, vs Marketer) • Editable by Campaign Manager or Super Admin only • Visible in reporting UIs and exports | MVP |  |  |  | #VALUE! | #VALUE! | S | 1
2. Campaign Orchestration | 2.7 Auto-Creation of Campaigns | • Enables automatic creation of campaign records based on: • Triggered rules (e.g., Salesforce stage = Closed Won) • API push (e.g., Integrate sends a new campaign record) • Campaigns are pre-filled with mapped fields from opportunity, forecast, or audience • Campaign Managers can review and approve auto-created drafts | Post-MVP | Salesforce | Salesforce |  | #VALUE! | #VALUE! | M | 2
2. Campaign Orchestration | 2.8 Forecast "Calculator" Via Audience | Swag forecast reach KPI with budgetary inputs. This is napkin math. Deploy behind a feature flag until we have enough certainty from bottom-up data analysis to support it. | MVP | [5 empty] | S | 1
3. Attribution & Reporting | 3.1 Reporting Tables | • Generate aggregated tables for Metabase. • Store in DB with timestamps. Send out billing 'payload' for business EDW consumption - ***Make separate row | MVP | 5.1, Metabase | Metabase | 3.2, 4.10 | #VALUE! | #VALUE! | XXL | 8 | need new feature for biz review
3. Attribution & Reporting | 3.2 Metabase Embed (UI) | • Embed Metabase dashboards via iFrame for results & statistics queried from TTD APIs and attribution reports. • Performance target: <2 second page loads. • Table1: Customer Analysis File • Table 2: Analytics File Needs to Join (?) •Table 3: Brand Reporting • Table 4: Customer Billing | MVP | 3.1, Metabase, TTD, 7.3 | Metabase, TTD | 3.1 | #VALUE! | #VALUE! | XL | 6
4. Data Integration: Bombaro | 4.1 File Ingestion Service | • Automates the daily ingestion of Bombora intent data delivered via S3 file drops • Validates file schema, ensures freshness (<24h), and surfaces ingestion errors • Feeds data into the Audience Builder and Attribution Engine for downstream use • Supports >20M records/day with processing target <2 hours • Operates as a backend-only service triggered on schedule and/or file event *Need to track total daily cookies for queries. | MVP | AWS S3, Bombora | AWS S3, Bombora | Audience Filed-Mapping Requirements | #VALUE! | #VALUE! | S | 1
4. Data Integration: Bombaro | 4.2 Taxonomy Mapping Engine | • Normalizes Bombora’s raw dimensions (topics, revenue, install base, etc.) into structured dimensions usable across features • Maps fields into system-wide reference tables for use in UI filters, segments, and reporting • Ensures consistent data usage across uploaded audiences and sourced Bombora cohorts • Built as a reusable mapping service for other third-party data providers in the future | MVP | Bombora | Bombora |  | #VALUE! | #VALUE! | S | 1
4. Data Integration: Bombaro | 4.3 Audience Expansion API | • Enables dynamic enrichment of user-uploaded audiences by cross-referencing Bombora behavioral data • Accepts input cohort and outputs a probabilistically matched segment using industry, topic, or function • Feeds into Forecast Engine and Audience Builder logic • Supports future use of intent scoring thresholds or trending signals (post mvp) | MVP | Bombora | Bombora |  | #VALUE! | #VALUE! | S | 1
4. Data Integration: TTD | 4.4 Campaign Sync API | • Translates P360 campaign objects (Programs, Campaigns, Line Items) into TTD-compatible JSON payloads • Pushes campaigns to TTD using authenticated service API keys • Supports updates, status polling, and TTD object lifecycle alignment • Includes retry logic and logging for failed API calls • Required for launching campaigns via the P360 UI | MVP | TTD | TTD |  | #VALUE! | #VALUE! | S | 1
4. Data Integration: TTD | 4.5 TTD REDS File Ingestion | • Ingests hourly REDS log files (TTD → P360) containing impression, click, and conversion events • Validates schema and joins REDS records with internal campaign IDs and Bombora enrichment • Used to power attribution logic and downstream reporting (Silver/Gold layers) • Targets <15 min latency per hourly file to keep reporting up-to-date | MVP | Bombora, TTD | Bombora, TTD, AWS Glue |  | #VALUE! | #VALUE! | M | 2 | 4 feeds w/ UIDs (Tanner)
4. Data Integration: TTD | 4.6 Identity Sync & Audience Export | • Normalizes account and persona data against bombora cookies • Batches or streams converted audiences to TTD audience API endpoints • Ensures identity sync across custom uploaded audiences and enriched Bombora segments | MVP | Bombora, TTD | Bombora, TTD | 1.5 | #VALUE! | #VALUE! | S | 1
4. Data Integration: TTD | 4.7 TTD Advertiser API Key Management | •Fetch advertiser ID from TTD to account - Ability for Super Admin to view ID/key • Keys are scoped per organization/seat and tied to campaign syncing workflows • Includes key rotation support, error alerting, and encrypted storage • Ensures clean separation of advertiser identity across clients | MVP | TTD | TTD |  | #VALUE! | #VALUE! | S | 1
4. Data Integration: Salesforce | 4.8 3x Daily Sync | • Sync Accounts/Opportunities/Line Items. • Conflict resolution (Salesforce takes priority by default). • Performance target: <15 minutes full sync. | MVP | Salesforce | Salesforce |  | #VALUE! | #VALUE! | M | 2
4. Data Integration: Salesforce | 4.9 On-Demand Sync | • User-triggered sync. • UI shows last sync time/status. | Post-MVP | 5.1 |  |  | #VALUE! | #VALUE! | S | 1 | evaluate API credits w/ Salesforce
4. Data Integration: Salesforce | 4.10 Billing Reconciliation Logic | • Joins campaign outcomes to Salesforce deals for billing. • Reconciles actual spend against forecasts and planned budgets, identifying discrepancies between planned and actual spend. • Provides Super Admin functionality for bulk recording of reconciled data to Salesforce - Campaigns cannot go active unless mapped | MVP | 5.1, Salesforce, 3.2 | Salesforce | 5.1 | #VALUE! | #VALUE! | M | 2
4. Data Integration: Salesforce | 4.11 Manual/Bulk Record Reconciliation | • Enables Super Admins to manually link unmapped Opportunities, Programs, and Campaigns in bulk via UI. • Ensures downstream syncs and billing accuracy by resolving orphaned records. • Supports filters by org, record type (Program/Campaign), and sync status. • Audit trail logs all reconciliation actions. | MVP | 4.7, 5.1 |  |  | #VALUE! | #VALUE! | S | 1
7. Advanced Data Management | 7.1 Audience Versioning & Rollback | • Allows users to view and restore previous versions of an audience. • Tracks changes made to audience segments over time, providing an audit trail and the ability to revert to an earlier state. Audience A = Unique Data Sourcing, A.1 = tweaks to existing resourcing, B = new data source for building the audience. | MVP | 1.2 |  |  | #VALUE! | #VALUE! | L | 4
5. Operational Support | 5.1 Basic User Onboarding Flow | • Initial user walkthrough to setup CSV upload, audience, and campaign configuration (minimal viable path). Tool tip/animation video to plug in. | MVP | 1.1, 1.2, 2.2 |  |  | #VALUE! | #VALUE! | S | 1
6. Performance Insights & Optimization | 6.1 Performance Summary Cards | • Aggregate KPIs across all programs with filters. | Post-MVP | 3.1 |  |  | #VALUE! | #VALUE! | S | 1
6. Performance Insights & Optimization | 6.2 Insight Tags & Annotations | • Tags like “Underperforming Audience”, “Budget Cap Hit”. | Post-MVP | 3.1 |  |  | #VALUE! | #VALUE! | M | 2
9. Extendibility & Scalability | 9.1 Open API for Custom Integrations | • Secure REST API that allows P360's internal teams or future partners to build custom integrations for campaign management, audience sync, or data ingestion. | Post-MVP |  |  |  | #VALUE! | #VALUE! | M | 2
10. Marketplace Management | 10.1 Seller Asset Listing & Management | • UI for sellers to upload assets (media kits, rate cards) to S3 with metadata (e.g., formats: JPEG/PDF, max 50MB/file). • Validates asset types and tags against P360’s marketplace taxonomy. • Performance target: <2s asset preview load; <30s bulk upload processing (max 20 files). • Integrates with 115.10 (Seller Role) for permission checks. | Post-MVP | AWS S3 | AWS S3 |  | #VALUE! | #VALUE! | XL | 6
13. Roles & Permissions | 13.1 Org Management UI | • Admins create orgs, link to TTD seats/Salesforce. • Audit trail for changes. • Entra ID mapping (internal/external, B2B entra) | MVP | 4.1, Microsoft Entra ID, Salesforce, TTD | Microsoft Entra ID, Salesforce, TTD | 6.1, 6.2 | #VALUE! | #VALUE! | S | 1
13. Roles & Permissions | 13.2 Super Admin (Internal Only) | • Internal role with full system privileges: org creation, API key management, user provisioning. • Can impersonate users for debugging. (Post MVP) • Defines and enforces role scopes (Buyer, Seller, Campaign Manager) | MVP | 4.1, 4.2 |  |  | #VALUE! | #VALUE! | M | 2
13. Roles & Permissions | 13.3 Campaign Manager (Internal Only) | • Internal team members assigned to customer accounts for campaign operations. • Can view/manage entities only in assigned orgs. • Can create/edit programs, audiences, campaigns • Can upload data and trigger syncs • Can manually reconcile unmapped records (Programs <-> Salesforce) • View reporting & campaign performance • Assigned access to multiple orgs but not global access | MVP | Salesforce | Salesforce |  | #VALUE! | #VALUE! | S | 1
13. Roles & Permissions | 13.4 Marketer / Buyer (External) | • External role for campaign configuration and reporting within their org. • Can upload audiences, generate forecasts, and draft campaigns (approval may be required). • No access to org management or seller data. | MVP | 4.6 |  |  | #VALUE! | #VALUE! | S | 1
7. Advanced Data Management | 7.2 Data Export & API Access | • Enables users to export raw or aggregated data (e.g., attribution reports, campaign metrics) in various formats (CSV, JSON) for external analysis. • Provides an API for programmatic data access. | Post-MVP | 3.1 |  |  | #VALUE! | #VALUE! | M | 2 | reporting client we determine (Dependency). Bounteous to provide recs.
7. Advanced Data Management | 7.3 Attribution Engine | • Join REDS + audience (1.2) + campaign (2.2) data. • Custom rules for reconciliation (e.g., match cookie_id to audience_id). | MVP | 1.2, 2.2 | Bombora, TTD | 3.1 | #VALUE! | #VALUE! | M | 2
8. User & System Activity Tracking | 8.1 Comprehensive Audit Trail (UI) | • Enhanced UI to view all user actions, system events, and data changes, beyond basic logging. • Includes filters, search capabilities, and detailed logs for compliance and troubleshooting. Logs for asset uploads, program creation, campaign state changes, record reconciliation, and API usage (incl. Integrate and TTD) Filters by org, feature, timestamp, user type (internal vs external) | MVP | 4.4, TTD | TTD |  | #VALUE! | #VALUE! | M | 2
8. User & System Activity Tracking | 8.2 User Audit Logging | • Comprehensive user audit logging – features write to service for history logs. Consumable via UI and CSV export. (DataDog, link to 8.1) | MVP | 4.1 |  | 1.1, 2.2 | #VALUE! | #VALUE! | M | 2
10. Marketplace Management | 10.4 Marketplace-Level Reporting Dashboard | • Seller dashboard showing asset performance (impressions, CTR) sourced from TTD and 3.1 (Reporting Tables). • Supports CSV export with <10s processing for 1M+ records. • Isolates data by org to prevent cross-seller visibility. | Post-MVP | TTD | TTD |  | #VALUE! | #VALUE! | M | 2
6. Performance Insights & Optimization | 6.3 Optimization Suggestion Engine | • Recommends bid, budget, creative tweaks via AI. | Post-MVP | 2.2 |  |  | #VALUE! | #VALUE! | XL | 6
10. Marketplace Management | 10.3 Cross-Org Content Syndication Rules | • Enables Super Admins/Sellers to syndicate assets to buyer orgs with rules (e.g., expiry dates, usage limits). • Logs syndication events to 10.1 (Audit Trail). • Performance target: <5s to apply rules to 100+ assets. | Post-MVP |  |  |  | #VALUE! | #VALUE! | XL | 6
12. Tech Foundation | 12.2 Multi-Tenant Auth | • Role-based access • Microsoft Entra ID for internal SSO • Supports multi-tenant user authentication and authorization. | MVP | Microsoft Entra ID | Microsoft Entra ID | 6.1, 6.2 | #VALUE! | #VALUE! |  |  | infra
12. Tech Foundation | 12.3 Data Security & Compliance | • Implement data encryption (at rest and in transit), access controls, and API security (OAuth 2.0, rate limiting, input validation). • Architecture to support GDPR, CCPA, and future SOC2 certification (2026). | MVP |  |  | 1.1, 3.1, 4.1, 4.3, 5.1, 12.4 | #VALUE! | #VALUE! |  |  | infra
10. Marketplace Management | 10.2 Buyer View of Marketplace | • Buyer-facing UI to filter seller offerings by vertical, audience size, and price range. • Pulls real-time availability data from TTD for activated audiences. • Performance target: <1.5s page load with 100+ listings; supports 50+ concurrent buyers. | Post-MVP | TTD | TTD |  | #VALUE! | #VALUE! | XL | 6
12. Tech Foundation | 12.4 Microsoft Entra ID SSO (Internal/External Only) | • Integrate Microsoft Entra ID via SAML/OIDC for internal P360 user authentication. • Map Entra ID groups to P360 internal org structure (teams, roles) | MVP | 4.1, Microsoft Entra ID | Microsoft Entra ID |  | #VALUE! | #VALUE! |  |  | infra
11. Integrate Sync Services | 11.1 Open API Endpoint for Integrate Campaign Sync | • RESTful POST/PUT endpoint for Integrate to push campaign | MVP |  |  | 2.7 | #VALUE! | #VALUE! | S | 1 | Tanner to clarify joins
11. Integrate Sync Services | 11.2 Campaign Result Push to Integrate | • Async/batch push of post-campaign performance and attribution data to Integrate. • Supports API (JSON) and webhook notifications for real-time updates. • Maps P360 attribution metrics to Integrate’s schema (e.g., impressions → Integrate_Campaign_ID) | Post-MVP | 11.1, 3.1 |  |  | #VALUE! | #VALUE! | S | 1 | Tanner to clarify joins
12. Tech Foundation | 12.1 REDS Data Ingestion | • Hourly S3 file processing from TTD (REDS). • Validate/log corrupted files. • Performance target: Hourly processing for REDS. | MVP | AWS S3, TTD | AWS S3, TTD | 3.2 | #VALUE! | #VALUE! | S | 1
12. Tech Foundation | 12.5 External User Authentication | • Configure external identity providers (Auth0, Okta) per tenant, with OIDC-based federated login. • Support MFA/OTP fallback for Marketers and small orgs. • Map external users to P360 orgs with granular permissions (Buyer/Seller/Agency). | MVP | 4.1, 4.4, Auth0/Okta | Auth0/Okta |  | #VALUE! | #VALUE! |  |  | Infra
12. Tech Foundation | 12.6 System Monitoring & Health Checks | • System monitoring and health checks – written on a feature-by-feature basis. Integration with monitoring and alerting systems. | MVP |  |  |  | #VALUE! | #VALUE! |  |  | INfra
12. Tech Foundation | 12.7 Sandbox/Test Mode | • Test mode where campaigns don't go live, bypassing sync to TTD. • Allows for safe testing and training. Environment management. Local, Staging, QA?, Prod | MVP | 4.1, TTD | TTD | 1.5, 2.4 | #VALUE! | #VALUE! |  |  | Infra
12. Tech Foundation | 12.8 Data Ingestion Monitoring (Basic version) | • Real-time dashboards and alerts for the status and health of all data ingestion pipelines (CSV, Bombora, REDS). • Includes metrics like record count, error rates, and processing latency. | MVP | 1.1, 1.3, 3.1, Bombora, 12.6 | Bombora |  | #VALUE! | #VALUE! |  |  | redundant to datadog features | infra
12. Tech Foundation | 12.9 Integration Health Dashboard (Basic version) | • Comprehensive view of API integration statuses (TTD, Salesforce), showing success rates, response times, and specific error logs for failed syncs or API calls. Alerts for sustained failures. | Post-MVP | 1.5, 2.4, 5.1, Salesforce, TTD | Salesforce, TTD, Bombora |  | #VALUE! | #VALUE! | M | 2
13. Roles & Permissions | 13.5 Seller (External) | • Partner persona who manages listings and assets within the Marketplace. Cannot access buyer-side campaign or reporting features. • Can upload and manage seller-side assets • Can view marketplace performance of their assets • Can configure content syndication rules • Cannot access campaigns, programs, or buyer PII | Post-MVP | 12.1 |  | 12.1–12.4 | #VALUE! | #VALUE! | XL | 6
13. Roles & Permissions | 13.6 Agency (External) | • Agencies managing campaigns across multiple buyers. May have read-only or edit access across orgs based on permissions. • Assigned to multiple customer orgs • Read-only access to campaign setup and reports • Cannot access seller features • Cannot manage billing or org setup | Post-MVP | 4.6 |  |  | #VALUE! | #VALUE! | XL | 6
14. Roles & Permissions | Conversion Pixel | A user needs to be able to retrieve a white labeled version of their TTD Advertiser Pixel for placement on their site in order to log conversions from the campaigns that they are running. | MVP | 4.6
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lean scope for MVP
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No bulk mvp
Note on E32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lean scope for MVP
Note on D35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added program configuration for pre-sales
Note on E38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lean scope for MVP
Note on D43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Early test results manually, fast.
Note on E44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lean scope for MVP
Note on E59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lean scope for MVP

## Traceability
https://miro.com/app/board/uXjVIkjtAqk=/?userEmail=nate.williams@bounteous.com&track=true&utm_source=notification&utm_medium=email&utm_campaign=add-to-board&utm_content=go-to-board&lid=6e2oe7utvsa4
Direct Dependency Management
Feature Mapping | Work Unit Type | Name | Units | D/S Dep (Tables + UI) | U/S Dep (Tables + UI) | Tot Dep | Check
1.1 CSV Upload & Ingestion | UI/Screen | Audience Import | 1 | 1 | 0 | 1 | 1.1 CSV Upload & Ingestion
1.3 Audience Field-Mapping Service | UI/Screen | Audience Field Mapping Service | 1 | 3 | 2 | 5 | 1.3 Audience Field-Mapping Service
1.2 Audience Builder | UI/Screen | Audience Builder | 1 | 3 | 2 | 5 | 1.2 Audience Builder
1.1 CSV Upload & Ingestion | Table/Integration | Audience Import | 1 | 0 | 0 | 0 | 1.1 CSV Upload & Ingestion
1.3 Audience Field-Mapping Service | Table/Integration | Audience Field Mapping Service | 1 | 3 | 2 | 5 | 1.3 Audience Field-Mapping Service
1.2 Audience Builder | Table/Integration | Account-Based Audience Config (JSON) | 1 | 1 | 1 | 2 | 1.2 Audience Builder
1.2 Audience Builder | Table/Integration | People-Based (JSON) | 1 | 1 | 1 | 2 | 1.2 Audience Builder
1.2 Audience Builder | Table/Integration | Audience Builder | 1 | 1 | 2 | 3 | 1.2 Audience Builder
4.1 File Ingestion Service | Table/Integration | Bombora (S3) | 1 | 1 | 0 | 1 | 4.1 File Ingestion Service
GAP - Sree to reconcile | Table/Integration | Integrate (Report/Org/Address) | 1 | 1 | 0 | 1 | #N/A
2.1 Program Hierarchy | UI/Screen | Programs | 1 | 2 | 1 | 3 | 2.1 Program Hierarchy
2.2 Campaign Configuration | UI/Screen | Campaigns | 1 | 3 | 1 | 4 | 2.2 Campaign Configuration
2.6 Campaign Metadata Enrichment | UI/Screen | Display Campaigns | 1 | 2 | 2 | 4 | 2.6 Campaign Metadata Enrichment
2.3 Line Item Configuration | UI/Screen | Display Line Item | 1 | 0 | 2 | 2 | 2.3 Line Item Configuration
2.1 Program Hierarchy | Table/Integration | Programs | 1 | 2 | 1 | 3 | 2.1 Program Hierarchy
2.2 Campaign Configuration | Table/Integration | Campaigns | 1 | 3 | 1 | 4 | 2.2 Campaign Configuration
2.6 Campaign Metadata Enrichment | Table/Integration | Display Campaigns | 1 | 2 | 2 | 4 | 2.6 Campaign Metadata Enrichment
2.3 Line Item Configuration | Table/Integration | Display Line Item | 1 | 0 | 2 | 2 | 2.3 Line Item Configuration
GAP - Sree to reconcile | Table/Integration | Customer - Organization | 1 | 1 | 1 | 2 | #N/A
4.8 3x Daily Sync | Table/Integration | Salesforce Account | 1 | 1 | 1 | 2 | 4.8 3x Daily Sync
4.8 3x Daily Sync | Table/Integration | Salesforce Opportunities | 1 | 4 | 1 | 5 | 4.8 3x Daily Sync
4.8 3x Daily Sync | Table/Integration | Salesforce Opportunity Cases | 1 | 0 | 1 | 1 | 4.8 3x Daily Sync
4.8 3x Daily Sync | Table/Integration | Salesforce Opportunity Product | 1 | 0 | 1 | 1 | 4.8 3x Daily Sync
4.8 3x Daily Sync | Table/Integration | Salesforce Opportunity Line Item | 1 | 1 | 1 | 2 | 4.8 3x Daily Sync
4.5 TTD REDS File Ingestion | Table/Integration | TTD REDS S3: Campaigns | 1 | 1 | 1 | 2 | 4.5 TTD REDS File Ingestion
4.5 TTD REDS File Ingestion | Table/Integration | TradeDesk Ad Group | 1 | 1 | 1 | 2 | 4.5 TTD REDS File Ingestion
11.1 Open API Endpoint for Integrate Campaign Sync | Table/Integration | Integrate Source | 1 | 0 | 1 | 1 | 11.1 Open API Endpoint for Integrate Campaign Sync
11.1 Open API Endpoint for Integrate Campaign Sync | Table/Integration | Integrate Campaign | 1 | 0 | 1 | 1 | 11.1 Open API Endpoint for Integrate Campaign Sync
11.1 Open API Endpoint for Integrate Campaign Sync | Table/Integration | Integrate Customer/Name | 1 | 1 | 1 | 2 | 11.1 Open API Endpoint for Integrate Campaign Sync
2.5 Forecast Generation Engine | UI/Screen | Forecasts | 1 | 2 | 3 | 5 | 2.5 Forecast Generation Engine
4.6 UID2 Identity Sync & Audience Export | Table/Integration | TTD Forecasts API | 1 | 1 | 1 | 2 | 4.6 UID2 Identity Sync & Audience Export
4.3 Audience Expansion API | Table/Integration | TTD Audience | 1 | 1 | 0 | 1 | 4.3 Audience Expansion API
4.2 Taxonomy Mapping Engine | Table/Integration | TTD Taxonomy Mapping API | 1 | 0 | 0 | 0 | 4.2 Taxonomy Mapping Engine
4.4 Campaign Sync API | Table/Integration | TTD Campaign Sync API | 1 | 0 | 0 | 0 | 4.4 Campaign Sync API
4.6 UID2 Identity Sync & Audience Export | Table/Integration | TTD Audience | 1 | 0 | 0 | 0 | 4.6 UID2 Identity Sync & Audience Export
4.7 TTD Advertiser API Key Management | Table/Integration | TTD Advertiser | 1 | 0 | 0 | 0 | 4.7 TTD Advertiser API Key Management
3.1 Reporting Tables | Table/Integration | Customer Analytics File | 1 | 1 | 3 | 4 | 3.1 Reporting Tables
3.1 Reporting Tables | Table/Integration | Analytics File Needs to Join | 1 | 1 | 4 | 5 | 3.1 Reporting Tables
3.1 Reporting Tables | Table/Integration | Brand Reporting | 1 | 1 | 5 | 6 | 3.1 Reporting Tables
3.1 Reporting Tables | Table/Integration | Customer Billing | 1 | 1 | 3 | 4 | 3.1 Reporting Tables
3.1 Reporting Tables | Table/Integration | Reference/Dim: Audience | 1 | 1 | 1 | 2 | 3.1 Reporting Tables
3.1 Reporting Tables | Table/Integration | Reference/Dim: Salesforce Hierarchy | 3 | 3 | 3 | 6 | 3.1 Reporting Tables
3.2 Metabase Embed (UI) | UI/Screen | Embedded Reporting | 1 | 0 | 4 | 4 | 3.2 Metabase Embed (UI)
5.1 Basic User Onboarding Flow | UI/Screen | Onboarding Workflow | 1 | 0 | 2 | 2 | 5.1 Basic User Onboarding Flow
6.1 Performance Summary Cards | UI/Screen | Performace Reporting | 1 | 0 | 2 | 2 | 6.1 Performance Summary Cards
6.2 Insight Tags & Annotations | UI/Screen | Insight Reporting | 1 | 0 | 2 | 2 | 6.2 Insight Tags & Annotations
6.3 Optimization Suggestion Engine | UI/Screen | Campaign Optimization Reporting | 1 | 0 | 2 | 2 | 6.3 Optimization Suggestion Engine
6.1 Performance Summary Cards | Table/Integration | Performace Reporting | 1 | 2 | 2 | 4 | 6.1 Performance Summary Cards
6.2 Insight Tags & Annotations | Table/Integration | Insight Reporting | 1 | 2 | 2 | 4 | 6.2 Insight Tags & Annotations
6.3 Optimization Suggestion Engine | Table/Integration | Campaign Optimization Reporting | 1 | 2 | 2 | 4 | 6.3 Optimization Suggestion Engine
7.1 Audience Versioning & Rollback | Table/Integration | Audiences: Change Tracking | 1 | 1 | 1 | 2 | 7.1 Audience Versioning & Rollback
7.2 Data Export & API Access | Table/Integration | Data Export/API Integration (Customers) | 5 | 5 | 0 | 5 | 7.2 Data Export & API Access
7.4 Field Mapping Engine | UI/Screen | Field Mapping Engine | 1 | 1 | 1 | 2 | #N/A
7.4 Field Mapping Engine | Table/Integration | Field Mapping Engine | 1 | 1 | 1 | 2 | #N/A
8.1 Comprehensive Audit Trail (UI) | UI/Screen | Comprehensive Audit Log | 1 | 30 | 1 | 31 | 8.1 Comprehensive Audit Trail (UI)
8.2 User Audit Logging | Table/Integration | Comprehensive Audit Log | 1 | 30 | 1 | 31 | 8.2 User Audit Logging
10.3 Cross-Org Content Syndication Rules | UI/Screen | Content Syndication Campaign | 1 | 1 | 2 | 3 | 10.3 Cross-Org Content Syndication Rules
10.3 Cross-Org Content Syndication Rules | UI/Screen | CS Line Item | 1 | 2 | 2 | 4 | 10.3 Cross-Org Content Syndication Rules
10.3 Cross-Org Content Syndication Rules | UI/Screen | Campaign Bids | 1 | 1 | 1 | 2 | 10.3 Cross-Org Content Syndication Rules
10.3 Cross-Org Content Syndication Rules | Table/Integration | Content Syndication Campaign | 1 | 1 | 2 | 3 | 10.3 Cross-Org Content Syndication Rules
10.3 Cross-Org Content Syndication Rules | Table/Integration | CS Line Item | 1 | 2 | 2 | 4 | 10.3 Cross-Org Content Syndication Rules
10.3 Cross-Org Content Syndication Rules | Table/Integration | Campaign Bids | 1 | 1 | 1 | 2 | 10.3 Cross-Org Content Syndication Rules
10.1 Seller Asset Listing & Management | UI/Screen | Marketplace Bidding Portal | 1 | 1 | 1 | 2 | 10.1 Seller Asset Listing & Management
10.4 Marketplace-Level Reporting Dashboard | UI/Screen | Marketplace Bidding Portal | 1 | 1 | 1 | 2 | 10.4 Marketplace-Level Reporting Dashboard
10.3 Cross-Org Content Syndication Rules | UI/Screen | Marketplace Bidding Portal | 1 | 1 | 1 | 2 | 10.3 Cross-Org Content Syndication Rules
10.2 Buyer View of Marketplace | UI/Screen | Marketplace Bidding Portal | 1 | 1 | 1 | 2 | 10.2 Buyer View of Marketplace
10.1 Seller Asset Listing & Management | Table/Integration | Marketplace Bidding Portal | 1 | 1 | 1 | 2 | 10.1 Seller Asset Listing & Management
10.4 Marketplace-Level Reporting Dashboard | Table/Integration | Marketplace Bidding Portal | 1 | 1 | 1 | 2 | 10.4 Marketplace-Level Reporting Dashboard
10.3 Cross-Org Content Syndication Rules | Table/Integration | Marketplace Bidding Portal | 1 | 1 | 1 | 2 | 10.3 Cross-Org Content Syndication Rules
10.2 Buyer View of Marketplace | Table/Integration | Marketplace Bidding Portal | 1 | 1 | 1 | 2 | 10.2 Buyer View of Marketplace
13.1 Org Management UI | UI/Screen | Org Management | 1 | 1 | 1 | 2 | 13.1 Org Management UI
13.2 Super Admin (Internal Only) | UI/Screen | Roles & Permissions Assignment | 1 | 1 | 1 | 2 | 13.2 Super Admin (Internal Only)
13.2 Super Admin (Internal Only) | UI/Screen | Standard Roles & Permissions Config (Features) | 0 | 1 | 1 | 2 | 13.2 Super Admin (Internal Only)
13.1 Org Management UI | Table/Integration | Org Management / Recon | 1 | 1 | 1 | 2 | 13.1 Org Management UI
13.2 Super Admin (Internal Only) | Table/Integration | Roles & Permissions Assignment | 1 | 1 | 1 | 2 | 13.2 Super Admin (Internal Only)
13.2 Super Admin (Internal Only) | Table/Integration | Standard Roles & Permissions Config (Features) | 1 | 1 | 1 | 2 | 13.2 Super Admin (Internal Only)
[6 empty] | 0 | #N/A
| Audience |  |  |  |  | 0 | #N/A
[6 empty] | 0 | #N/A
[6 empty] | 0 | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Campaign Orchestration
Attribution & Reporting
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Feature 11 is integrate sync services. Can you please review the data sources to ensure mapping in the feature set is 1-1? @Sreenath Kurupath
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One for MVP, w/out media marketplace.
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sreenath Kurupath - confirm feature mapping.
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: One for MVP, w/out media marketplace.
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sreenath Kurupath - confirm feature mapping.
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Opp line item not represented in ERD for connection.
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There’s notes on GraphQL sync API, but also S3 bucket...which is it? Both?
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I don’t know if this is an accurate mapping, unclear from my end. @Sreenath Kurupath - please review.
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add to data integration integrate feature (doesn’t exist).
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: I’m not seeing the forecasts API in the TTD rows, @Sreenath Kurupath - please advise.
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are campaigns synced via S3 drop, API, or both?
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this redundant to audience expansion API? Reply: Comments on batch vs stream, can it be both?
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Roles and permissions, or where does this exist on ERD?
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed every key in the tables was a dependency.
Note on B48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assuming this is packaging up the app in a turbotax light flow, no new screens just guided tutorial?
Note on B55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same screen/ui, assuming additional change-tracking table for audience.
Note on B60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumed broad requirement for system, with key workflows elevated to traceability across the system.
Note on B61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sreenath Kurupath - please review the marketplace capability end to end to ensure this is articulated accurately.
Note on B62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sreenath Kurupath - please review the marketplace capability end to end to ensure this is articulated accurately.
Note on B63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sreenath Kurupath - please review the marketplace capability end to end to ensure this is articulated accurately.
Note on B64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sreenath Kurupath - please review the marketplace capability end to end to ensure this is articulated accurately.
Note on B65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sreenath Kurupath - please review the marketplace capability end to end to ensure this is articulated accurately.
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sreenath Kurupath - please review the marketplace capability end to end to ensure this is articulated accurately.
Note on E77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Back-end for MVP.

## UC Summary
| MVP |  |  | Demand
Use Case / Capability | Features | Screens | Tables | Wks | % Total
3. Attribution & Reporting | 2 | 1 | 8 | 14 | 23.33% | x
1. Audience Management | 5 | 3 | 5 | 9 | 15%
2. Campaign Orchestration | 8 | 4 | 4 | 7 | 11.67% | x
7. Advanced Data Management | 3 | 0 | 1 | 6 | 10%
4. Data Integration: TTD | 4 | 0 | 6 | 5 | 8.333% | x
4. Data Integration: Salesforce | 4 | 0 | 5 | 5 | 8.333%
13. Roles & Permissions | 6 | 2 | 3 | 5 | 8.333% | x | 55% reusable for for marketplace
8. User & System Activity Tracking | 2 | 1 | 1 | 4 | 6.667% | x
4. Data Integration: Bombaro | 3 | 0 | 3 | 3 | 5%
5. Operational Support | 1 | 1 | 0 | 1 | 1.667%
11. Integrate Sync Services | 2 | 0 | 3 | 1 | 1.667%
12. Tech Foundation | 9 | 0 | 0 | 0 | 0%
6. Performance Insights & Optimization | 3 | 0 | 0 | 0 | 0%
10. Marketplace Management | 4 | 0 | 0 | 0 | 0%
9. Extendibility & Scalability | 1 | 0 | 0 | 0 | 0%
Total | 57 | 12 | 39 | 60 | 100%
Supply | FTEs | Sprints | Dev/Wk/sp | Eng Weeks
Back-End/App Integration/API | 3 | 5 | 1.6 | 24
Full Stack/Front-End | 2 | 5 | 1.6 | 16
BI/Data | 3 | 5 | 1.6 | 24
| 8 |  |  | 64
-4
*Focuses on core feature dev work
**Discounts Infra/DevOps/Foundation/Product/QA, managed as ratios to dev team
Use Case / Capability | Features | Screens | Tables | Wks | % Total
Audience Management | 7 | 3 | 6 | 15 | 25%
Attribution, Reporting, & Adv Data Mgmt | 3 | 1 | 8 | 14 | 23.33%
Data Integration | 13 | 0 | 17 | 14 | 23.33%
Campaign Orchestration | 8 | 4 | 4 | 7 | 11.67%
Roles & Permissions | 6 | 2 | 3 | 5 | 8.333%
User & System Activity | 2 | 1 | 1 | 4 | 6.667%
Onboarding | 1 | 1 | 0 | 1 | 1.667%
|  | 12 | 39 | 60 | 100%

## DRAFT AI Use Cases
Use Case Area | Feature | AI Use Case | HL Description
Audience Management | Audience Deduplication | ML-Based Fuzzy Deduplication | Uses NLP and clustering to identify and flag near-duplicate domains or company names in CSV uploads and Bombora data, improving targeting accuracy and reducing redundant outreach.
Audience Management | Audience Field-Mapping | Dynamic Schema Mapping | Priy
Audience Management | Audience Export to TTD | Privacy-Safe UID2 Identity | Normalizes UID2 identifiers for TTD exports, ensuring GDPR/CCPA compliance. Logs mismatches for audit trails.
Audience Management | Audience Builder | AI-Powered Segment Suggestions | Recommends new audience segments based on analysis of historical campaign performance, Bombora intent, and existing audience attributes using vector embeddings for similarity.
Campaign Orchestration | Forecast Generation | Predictive Reach & Pacing | Forecasts campaign reach and pacing over time by analyzing historical campaign data, market trends, and audience size to inform budget planning.
Campaign Orchestration | Future: Optimization Engine | Real-Time Bid/Budget Optimizer | Analyzes live campaign data (REDS + TTD) to recommend optimal bid adjustments, pacing, or budget reallocation to maximize campaign efficiency.
Data Integration: Salesforce | Manual/Bulk Record | Automated Record Matching Engine | Uses fuzzy matching and ML heuristics to suggest mappings between orphaned P360 campaigns and Salesforce opportunities, including conflict resolution logic.
Marketplace Management | Future: Creative Review | Creative Compliance Classifier | Flags policy/brand violations in seller-uploaded assets (JPEG/PDF) using NLP and image analysis, preventing non-compliant listings.
Attribution & Reporting | REDS Data Ingestion | Anomaly Detection for TTD Logs | Monitors hourly REDS files for anomalies (e.g., sudden impression drops, spike in invalid clicks), triggering alerts for campaign managers.
Campaign Orchestration | Campaign Configuration | Dynamic Budget Allocation Advisor | Recommends optimal budget shifts across line items within a campaign based on real-time performance (CTR, spend vs. forecast), integrating directly with TTD sync for automated adjustments.
Tech Foundation | Content Moderation | Automated Content Tagging | Automatically tags campaign creatives (images, text) with relevant categories (e.g., industry, tone, product type) to enhance searchability and facilitate compliance checks.
Advanced Data Management | Audience Versioning | Audience Logic Auto-Suggestions | Provides AI-driven suggestions for optimizing or expanding audience logic within the Audience Builder, drawing insights from successful past campaigns and data trends.
User & System Activity | Comprehensive Audit | Anomaly Detection for Audit Trail | Identifies unusual user activities or system events in the audit trail (e.g., suspicious logins, unauthorized data access) that could indicate security threats.
Operational Support | Basic User Onboarding | Intelligent Onboarding Assistant | Provides personalized guidance and interactive walkthroughs for new users, leveraging AI to adapt to user roles and initial setup needs (e.g., first CSV upload, campaign creation).
Campaign Orchestration | Line Item Configuration | AI-Driven Creative Optimization | Analyzes creative performance data (e.g., CTR, conversion rates by audience/context) to recommend optimal creative variations or suggest improvements for better engagement.

## INT OLD Use Cases & Features
Capability | Use Cases | Features | Description | Release (Day1) | Dependencies | Integrations | Cross-Feature Impact | P360 Requirements Reference | Screens | Tables/Ints | Questions/Complexity Drivers | T-Shirt | Eng Weeks
Audience Management | 1. Audience Management | 1.1 CSV Upload & Ingestion | • Users upload .csv of domains; system validates (format, duplicates) and stores in S3. Max 10K records/file; <30s processing. • Error log/management for failed imports **Discussion Point: Account name matching to domain (might require fuzzy matching, might not be MVP). Also, Domain + Country (CNN US vs UK, etc). AI potential | MVP | AWS S3 | AWS S3 | 1.2, 1.3, 1.5, 2.2 | • Core Requirements - User Management - Organization Management | 1 | 1 | Future Integration Points? | S | 1
Audience Management | 1. Audience Management | 1.2 Audience Builder | • AND/OR logic tree to segment data from CSV + Bombora fields (e.g., intent data). • Supports TTD-compatible JSON output. *Status/Change Log w/ revert back to previous audience, etc. Ability to view historical audience builds. | MVP | 1.1, 1.3, Bombora, TTD | Bombora, TTD | 1.5, 2.2 |  | 1 | 3 |  | L | 4
Audience Management | 1. Audience Management | 1.3 Audience Field-Mapping Service | • Ingests and normalizes Bombora S3 files (20–60M records/day) using predefined schema mappings (e.g., Bombora’s "company_name" → P360’s "account_name"). • Normalize fields (e.g., company_name, intent_data) for segmentation. Validates data against P360’s taxonomy (e.g., industry verticals, revenue tiers) • Real-time ingestion with validation. • Performance target: Vendor data processing within 4 hours. log mismatches for manual review. | MVP | 1.1, 4.4, AWS S3, Bombora | AWS S3, Bombora, Integrate | 1.2 |  | 1 | 1 | Assumes user table and role table | M | 2
Audience Management | 1. Audience Management | 1.4 Audience Deduplication | • Auto-flag duplicate audiences/invalid domains. Invalid Domains = Format (future: company doesn't exist, but out of scope) | MVP | 1.2 |  | 1.5 | • Core Requirements - User Management - Organization Management | 0 | 0 | • Are seat-org mappings stored by P360, or retrieved in real-time from TTD? | S | 1
Audience Management | 1. Audience Management | 1.5 Audience Export to TTD | • Convert audience segments to TTD-compatible JSON with UID2 identifiers for cookieless targeting. • Enrich payloads with first-party cookies (if available) and TTD field mappings (e.g., "P360_audience_id" → "ttd_segment_id"). • Implement retry logic for API failures (max 3 attempts) with exponential backoff. - When does an audience get updated? An audience in tradedesk gets updated upon save in audience builder, full weekly saturation / update from bombora on saturdays. Create tradedesk audience for every audience that's configured in P360. | MVP | 1.2, 6.1, TTD, UID2 | TTD, UID2, AWS S3 | 2.4 |  | 0 | 0 |  | S | 1
Campaign Orchestration | 2. Campaign Orchestration | 2.1 Program Hierarchy | • UI to nest Programs > Campaigns > Line Items. • DB schema supports parent-child relationships. - At some point, programs will need to hold files (non-mvp, but nice-to-have) - Program --> IO, Campaign --> Line Item | MVP |  |  | 2.2, 2.3 |  | 1 | 1 |  | M | 2
Campaign Orchestration | 2. Campaign Orchestration | 2.2 Campaign Configuration | • Set budget, flight dates, KPIs, and assign audiences (from 1.2). • Real-time validation (e.g., budget ≤ Program cap). Status / creation based off status, errors for Uis | MVP | 1.2, 2.1 |  | 2.4, 2.5 |  | 1 | 1 |  | S | 1
Campaign Orchestration | 2. Campaign Orchestration | 2.3 Line Item Configuration | • Configure bids, creatives, pacing. • Validate against TTD constraints (e.g., MaxBidCPM). - Line item configs are optional (nullable, etc) | MVP | 2.2, TTD | TTD | 2.4 |  | 1 | 1 |  | S | 1
Campaign Orchestration | 2. Campaign Orchestration | 2.4 Campaign Sync to TTD | • Call TTD APIs (/v3/campaign, /v3/adgroup). • Retry logic for API failures. • Log sync status. • Performance target: <5 seconds response for campaign actions. | MVP | 2.2, 2.3, TTD | TTD, 4.7 | 1.5 | • Core Requirements - Audience Building and Management • Performance Requirements - Customer File Uploads • Import Table = Audience Import • Service = Audience Field Mapping | 0 | 0 | • How do we manage and intake multiple file formats? Is the customer expected to conform or do we have to onboard? If the latter, how can we scale this process either via UI/mapping, or templatized IaC to ingest custom data? • How do custom audiences blend with P360 audiences? Is it either A or B, or is C = A + B hybrid required for audience building? • Confirm flow / screens / tables • Data validation layer - what are the requirements? • What's the error management experience look like? • What are the expected error states for CSV uploads (e.g., malformed headers, duplicate domains)? How should they be surfaced to users? | S | 1
Campaign Orchestration | 2. Campaign Orchestration | 2.5 Forecast Generation Engine | • Allows users (internal or buyer) to generate media delivery forecasts by combining TTD reach estimates with audience inputs (size, duration, geography, industry vertical) • Accepts inputs such as audience size, duration, geography, industry vertical, etc. • Returns estimated reach, impressions, match rate, and delivery window (confidence interval ±10%). • Can be run pre-campaign, post-audience creation • Should support multiple forecast versions per campaign • Stores forecasts in Program/Campaign records with versioning (max 5 versions per campaign). • Required as part of buyer-facing media plan review workflow • Performance target: <3s response time for forecasts with audiences <100K domains. • Validates inputs against TTD constraints (e.g., min/max budget, geo availability). | Post-MVP | 1.2, TTD, 2.2 | TTD |  | • Core Requirements - Audience Building and Management • Table1: Account-Based Audience Config • Table2: People-Based Audience Config • Table 3: Audience Builder (Output) | 1 | 0 | • This is the work for the screen that was demonstrated to build the audiences in the 7/30 demo. The nested and/or statements for filtering is the key BE complexity driver to ensure we pull the correct audience. Assuming there is a need to integrate multiple BE tables from P360 and Custom for this logic. • Should logic UI support nested logic? | L | 4
Campaign Orchestration | 2. Campaign Orchestration | 2.6 Campaign Metadata Enrichment | • Add optional metadata fields to campaigns: • Campaign Type (Display, Syndication, Marketplace) • Read/Write state based on role (Campaign Manager, vs Marketer) • Editable by Campaign Manager or Super Admin only • Visible in reporting UIs and exports | MVP |  |  |  | • Core Requirements - Data Processing Infrastructure • Core Requirements - Audience Building and Management • Performance Requirements - Vendor Data Processing Integrate sync for program and campaigns | 1 | 1 | • Blending data from 3 sources into a coherent table structure to enable audience building, need to dig into data quality management and rules here a bit more. • Will P360 supply a schema or mapping template for Bombora? | S | 1
Campaign Orchestration | 2. Campaign Orchestration | 2.7 Auto-Creation of Campaigns | • Enables automatic creation of campaign records based on: • Triggered rules (e.g., Salesforce stage = Closed Won) • API push (e.g., Integrate sends a new campaign record) • Campaigns are pre-filled with mapped fields from opportunity, forecast, or audience • Campaign Managers can review and approve auto-created drafts | Post-MVP | Salesforce | Salesforce |  | • Core Requirements - Audience Building and Management | 0 | 0 |  | M | 2
Campaign Orchestration | 2. Campaign Orchestration | 2.8 Forecast "Calculator" Via Audience | Swag forecast reach KPI with budgetary inputs. This is napkin math. Deploy behind a feature flag until we have enough certainty from bottom-up data analysis to support it. | MVP | [7 empty] | S | 1
Attribution, Reporting, & Adv Data Mgmt | 3. Attribution & Reporting | 3.1 Reporting Tables | • Generate aggregated tables for Metabase. • Store in DB with timestamps. Send out billing 'payload' for business EDW consumption - ***Make separate row | MVP | 5.1, Metabase | Metabase | 3.2, 4.10 | • Core Requirements - Integration Layer - TTD API Integration • Core Requirements - Audience Building and Management | 0 | 8 | • Confirm 1-way "push" to TTD vs any bi-directional sync requirements • Should audiences be versioned or overwritten? | XXL | 8 | need new feature for biz review
Attribution, Reporting, & Adv Data Mgmt | 3. Attribution & Reporting | 3.2 Metabase Embed (UI) | • Embed Metabase dashboards via iFrame for results & statistics queried from TTD APIs and attribution reports. • Performance target: <2 second page loads. • Table1: Customer Analysis File • Table 2: Analytics File Needs to Join (?) •Table 3: Brand Reporting • Table 4: Customer Billing | MVP | 3.1, Metabase, TTD, 7.3 | Metabase, TTD | 3.1 | • Core Requirements - Program & Campaign Management Table: Program | 1 | 0 | Is this UI multiple screens or one screen? I think 1 based on the ERD flagging separate screens at every level. This is the program level screen | XL | 6
Data Integration | 4. Data Integration: Bombaro | 4.1 File Ingestion Service | • Automates the daily ingestion of Bombora intent data delivered via S3 file drops • Validates file schema, ensures freshness (<24h), and surfaces ingestion errors • Feeds data into the Audience Builder and Attribution Engine for downstream use • Supports >20M records/day with processing target <2 hours • Operates as a backend-only service triggered on schedule and/or file event *Need to track total daily cookies for queries. | MVP | AWS S3, Bombora | AWS S3, Bombora | Audience Filed-Mapping Requirements | • Core Requirements - Program & Campaign Management Table1: Campaigns Table2: Display Campaign Table3: Campaigns (via REDS) | 0 | 1 | What about hierarchical campaign strategies for management and reporting? | S | 1
Data Integration | 4. Data Integration: Bombaro | 4.2 Taxonomy Mapping Engine | • Normalizes Bombora’s raw dimensions (topics, revenue, install base, etc.) into structured dimensions usable across features • Maps fields into system-wide reference tables for use in UI filters, segments, and reporting • Ensures consistent data usage across uploaded audiences and sourced Bombora cohorts • Built as a reusable mapping service for other third-party data providers in the future | MVP | Bombora | Bombora |  | • Core Requirements - Program & Campaign Management | 0 | 1 | • What granularity is required for pacing/creative assignment? • Are there TTD specific constraints (e.g., min/max bids) that should be enforced in the UI? | S | 1
Data Integration | 4. Data Integration: Bombaro | 4.3 Audience Expansion API | • Enables dynamic enrichment of user-uploaded audiences by cross-referencing Bombora behavioral data • Accepts input cohort and outputs a probabilistically matched segment using industry, topic, or function • Feeds into Forecast Engine and Audience Builder logic • Supports future use of intent scoring thresholds or trending signals (post mvp) | MVP | Bombora | Bombora |  | • Core Requirements - Integration Layer - TTD API Integration • Performance Requirements - Campaign Actions | 0 | 1 | Documented here is the OB flow back to TTD (vs inbound via S3). Might make sense to combine 2.4 and 2.2 into a single feature set. | S | 1
Data Integration | 4. Data Integration: TTD | 4.4 Campaign Sync API | • Translates P360 campaign objects (Programs, Campaigns, Line Items) into TTD-compatible JSON payloads • Pushes campaigns to TTD using authenticated service API keys • Supports updates, status polling, and TTD object lifecycle alignment • Includes retry logic and logging for failed API calls • Required for launching campaigns via the P360 UI | MVP | TTD | TTD |  | Table1: Forecasts Table2: TTD Forecast (API, Bi-Directional) Table 3: TTD Audience Dependent upon Audience Builder | 0 | 1 | Bi-directional sync w/ TTD | S | 1
Data Integration | 4. Data Integration: TTD | 4.5 TTD REDS File Ingestion | • Ingests hourly REDS log files (TTD → P360) containing impression, click, and conversion events • Validates schema and joins REDS records with internal campaign IDs and Bombora enrichment • Used to power attribution logic and downstream reporting (Silver/Gold layers) • Targets <15 min latency per hourly file to keep reporting up-to-date | MVP | Bombora, TTD | Bombora, TTD, AWS Glue |  |  | 0 | 2 |  | M | 2 | 4 feeds w/ UIDs (Tanner)
Data Integration | 4. Data Integration: TTD | 4.6 UID2 Identity Sync & Audience Export | • Normalizes account and persona data against bombora cookies • Batches or streams converted audiences to TTD audience API endpoints • Ensures identity sync across custom uploaded audiences and enriched Bombora segments | MVP | Bombora, TTD, UID2 | Bombora, TTD, UID2 | 1.5 |  | 0 | 2 |  | S | 1
Data Integration | 4. Data Integration: TTD | 4.7 TTD Advertiser API Key Management | •Fetch advertiser ID from TTD to account - Ability for Super Admin to view ID/key • Keys are scoped per organization/seat and tied to campaign syncing workflows • Includes key rotation support, error alerting, and encrypted storage • Ensures clean separation of advertiser identity across clients | MVP | TTD | TTD |  | • Core Requirements - Integration Layer - Salesforce Integration | 0 | 1 | • Are mappings static or user-configurable? What rules for conflict resolution? • Which Salesforce fields are mandatory for sync? Should empty values overwrite existing data? | S | 1
Data Integration | 4. Data Integration: Salesforce | 4.8 3x Daily Sync | • Sync Accounts/Opportunities/Line Items. • Conflict resolution (Salesforce takes priority by default). • Performance target: <15 minutes full sync. | MVP | Salesforce | Salesforce |  | • Core Requirements - Reporting & Analytics - Billing Integration (Implicit) | 0 | 5 | • Are all campaigns billable? How is partial attribution handled? | M | 2
Data Integration | 4. Data Integration: Salesforce | 4.9 On-Demand Sync | • User-triggered sync. • UI shows last sync time/status. | Post-MVP | 5.1 |  |  |  | 0 | 0 |  | S | 1 | evaluate API credits w/ Salesforce
Data Integration | 4. Data Integration: Salesforce | 4.10 Billing Reconciliation Logic | • Joins campaign outcomes to Salesforce deals for billing. • Reconciles actual spend against forecasts and planned budgets, identifying discrepancies between planned and actual spend. • Provides Super Admin functionality for bulk recording of reconciled data to Salesforce - Campaigns cannot go active unless mapped | MVP | 5.1, Salesforce, 3.2 | Salesforce | 5.1 | • Core Requirements - Audience Building and Management • Compliance Requirements - Data Governance (Implicit) | 0 | 0 | Does a UI exist for recon? New screen or on existing screen? | M | 2
Data Integration | 4. Data Integration: Salesforce | 4.11 Manual/Bulk Record Reconciliation | • Enables Super Admins to manually link unmapped Opportunities, Programs, and Campaigns in bulk via UI. • Ensures downstream syncs and billing accuracy by resolving orphaned records. • Supports filters by org, record type (Program/Campaign), and sync status. • Audit trail logs all reconciliation actions. | MVP | 4.7, 5.1 |  |  | • Core Requirements - Reporting & Analytics • Core Requirements - Integration Layer - API Access (Implicit) • Technical Architecture - Data Access | 0 | 0 | Does a UI exist for recon? New screen or on existing screen? | S | 1
Audience Management | 7. Advanced Data Management | 7.1 Audience Versioning & Rollback | • Allows users to view and restore previous versions of an audience. • Tracks changes made to audience segments over time, providing an audit trail and the ability to revert to an earlier state. Audience A = Unique Data Sourcing, A.1 = tweaks to existing resourcing, B = new data source for building the audience. | MVP | 1.2 |  |  | • Core Requirements - Reporting & Analytics - Attribution Logic | 0 | 1 | • Is it strictly rules-based for MVP, or hybrid with predictive inputs? • Should attribution rules be configurable by P360 admins, or hardcoded for MVP? | L | 4
Onboarding | 5. Operational Support | 5.1 Basic User Onboarding Flow | • Initial user walkthrough to setup CSV upload, audience, and campaign configuration (minimal viable path). Tool tip/animation video to plug in. | MVP | 1.1, 1.2, 2.2 |  |  | • Core Requirements - Reporting & Analytics | 1 | 0 |  | S | 1
Performance Insights & Optimization | 6. Performance Insights & Optimization | 6.1 Performance Summary Cards | • Aggregate KPIs across all programs with filters. | Post-MVP | 3.1 |  |  | • Core Requirements - Reporting & Analytics • Performance Requirements - UI Page Loads | 1 | 1 | • Should this support filter interactivity or just static views? - [Nate] sounds like they want self service a bit where customers can build their own journey, likely with defaults as well. Billing is floating in space, where is this sourced from? Need to understand bronze/silver/gold layer reporting for table counts and where each table is sourced from to come up with full table counts. Also, one dashboard or many? | S | 1
Performance Insights & Optimization | 6. Performance Insights & Optimization | 6.2 Insight Tags & Annotations | • Tags like “Underperforming Audience”, “Budget Cap Hit”. | Post-MVP | 3.1 |  |  | • User Experience (Implicit) | 1 | 1 |  | M | 2
Tech Foundation | 9. Extendibility & Scalability | 9.1 Open API for Custom Integrations | • Secure REST API that allows P360's internal teams or future partners to build custom integrations for campaign management, audience sync, or data ingestion. | Post-MVP |  |  |  | • Core Requirements - Integration Layer - Salesforce Integration • Performance Requirements - Salesforce Sync | 0 | 0 |  | M | 2
Marketplace Mgmt | 10. Marketplace Management | 10.1 Seller Asset Listing & Management | • UI for sellers to upload assets (media kits, rate cards) to S3 with metadata (e.g., formats: JPEG/PDF, max 50MB/file). • Validates asset types and tags against P360’s marketplace taxonomy. • Performance target: <2s asset preview load; <30s bulk upload processing (max 20 files). • Integrates with 115.10 (Seller Role) for permission checks. | Post-MVP | AWS S3 | AWS S3 |  | • Core Requirements - Integration Layer - Salesforce Integration | 1 | 1 |  | XL | 6
Roles & Permissions | 13. Roles & Permissions | 13.1 Org Management UI | • Admins create orgs, link to TTD seats/Salesforce. • Audit trail for changes. • Entra ID mapping (internal/external, B2B entra) | MVP | 4.1, Microsoft Entra ID, Salesforce, TTD | Microsoft Entra ID, Salesforce, TTD | 6.1, 6.2 |  | 1 | 1 |  | S | 1
Roles & Permissions | 13. Roles & Permissions | 13.2 Super Admin (Internal Only) | • Internal role with full system privileges: org creation, API key management, user provisioning. • Can impersonate users for debugging. (Post MVP) • Defines and enforces role scopes (Buyer, Seller, Campaign Manager) | MVP | 4.1, 4.2 |  |  |  | 1 | 2 |  | M | 2
Roles & Permissions | 13. Roles & Permissions | 13.3 Campaign Manager (Internal Only) | • Internal team members assigned to customer accounts for campaign operations. • Can view/manage entities only in assigned orgs. • Can create/edit programs, audiences, campaigns • Can upload data and trigger syncs • Can manually reconcile unmapped records (Programs <-> Salesforce) • View reporting & campaign performance • Assigned access to multiple orgs but not global access | MVP | Salesforce | Salesforce |  |  | 0 | 0 |  | S | 1
Roles & Permissions | 13. Roles & Permissions | 13.4 Marketer / Buyer (External) | • External role for campaign configuration and reporting within their org. • Can upload audiences, generate forecasts, and draft campaigns (approval may be required). • No access to org management or seller data. | MVP | 4.6 |  |  |  | 0 | 0 |  | S | 1
Attribution, Reporting, & Adv Data Mgmt | 7. Advanced Data Management | 7.2 Data Export & API Access | • Enables users to export raw or aggregated data (e.g., attribution reports, campaign metrics) in various formats (CSV, JSON) for external analysis. • Provides an API for programmatic data access. | Post-MVP | 3.1 |  |  | • Core Requirements - User Management - Roles and Permissions • Security Requirements - User Authentication | 0 | 5 |  | M | 2 | reporting client we determine (Dependency). Bounteous to provide recs.
Audience Management | 7. Advanced Data Management | 7.3 Attribution Engine | • Join REDS + audience (1.2) + campaign (2.2) data. • Custom rules for reconciliation (e.g., match cookie_id to audience_id). | MVP | 1.2, 2.2 | Bombora, TTD | 3.1 | • Security Requirements - Single Sign-On (SSO) | 0 | 0 | Does auth match w/ Customer Domain/Tables? How does this sync up? | M | 2
User & System Activity | 8. User & System Activity Tracking | 8.1 Comprehensive Audit Trail (UI) | • Enhanced UI to view all user actions, system events, and data changes, beyond basic logging. • Includes filters, search capabilities, and detailed logs for compliance and troubleshooting. Logs for asset uploads, program creation, campaign state changes, record reconciliation, and API usage (incl. Integrate and TTD) Filters by org, feature, timestamp, user type (internal vs external) | MVP | 4.4, TTD | TTD |  |  | 1 | 0 | Confirm Entra for internal/external vs internal. Assuming two tables (need tech input). Roles + permissions, security/user table. This way roles will be standard configurations | M | 2
User & System Activity | 8. User & System Activity Tracking | 8.2 User Audit Logging | • Comprehensive user audit logging – features write to service for history logs. Consumable via UI and CSV export. (DataDog, link to 8.1) | MVP | 4.1 |  | 1.1, 2.2 |  | 0 | 1 |  | M | 2
Marketplace Mgmt | 10. Marketplace Management | 10.4 Marketplace-Level Reporting Dashboard | • Seller dashboard showing asset performance (impressions, CTR) sourced from TTD and 3.1 (Reporting Tables). • Supports CSV export with <10s processing for 1M+ records. • Isolates data by org to prevent cross-seller visibility. | Post-MVP | TTD | TTD |  | • Technical Architecture - Development Environments (Implicit) | 1 | 1 | • Should sandbox campaigns persist in the DB like live campaigns, or be temporary? | M | 2
Performance Insights & Optimization | 6. Performance Insights & Optimization | 6.3 Optimization Suggestion Engine | • Recommends bid, budget, creative tweaks via AI. | Post-MVP | 2.2 |  |  | • Core Requirements - Data Processing Infrastructure • Core Requirements - Reporting & Analytics - Data Sources | 1 | 1 | This may be redundant to the other campaign orchestration work | XL | 6
Marketplace Mgmt | 10. Marketplace Management | 10.3 Cross-Org Content Syndication Rules | • Enables Super Admins/Sellers to syndicate assets to buyer orgs with rules (e.g., expiry dates, usage limits). • Logs syndication events to 10.1 (Audit Trail). • Performance target: <5s to apply rules to 100+ assets. | Post-MVP |  |  |  | • Technical Architecture - Monitoring and Alerting | 4 | 4 |  | XL | 6
Tech Foundation | 12. Tech Foundation | 12.2 Multi-Tenant Auth | • Role-based access • Microsoft Entra ID for internal SSO • Supports multi-tenant user authentication and authorization. | MVP | Microsoft Entra ID | Microsoft Entra ID | 6.1, 6.2 | • Technical Architecture - Monitoring and Alerting • Performance Requirements | 0 | 0 |  |  |  | infra
Tech Foundation | 12. Tech Foundation | 12.3 Data Security & Compliance | • Implement data encryption (at rest and in transit), access controls, and API security (OAuth 2.0, rate limiting, input validation). • Architecture to support GDPR, CCPA, and future SOC2 certification (2026). | MVP |  |  | 1.1, 3.1, 4.1, 4.3, 5.1, 12.4 | • Technical Architecture - Monitoring and Alerting • Core Requirements - Integration Layer | 0 | 0 |  |  |  | infra
Marketplace Mgmt | 10. Marketplace Management | 10.2 Buyer View of Marketplace | • Buyer-facing UI to filter seller offerings by vertical, audience size, and price range. • Pulls real-time availability data from TTD for activated audiences. • Performance target: <1.5s page load with 100+ listings; supports 50+ concurrent buyers. | Post-MVP | TTD | TTD |  | • Security Requirements - Audit Logging | 1 | 1 | • Should logs be filterable by feature/action? What retention is needed? Can we implement a standard tool for this vs custom build? Need to evaluate time/price tradeoff, but generally they are "cheap"? | XL | 6
Tech Foundation | 12. Tech Foundation | 12.4 Microsoft Entra ID SSO (Internal/External Only) | • Integrate Microsoft Entra ID via SAML/OIDC for internal P360 user authentication. • Map Entra ID groups to P360 internal org structure (teams, roles) | MVP | 4.1, Microsoft Entra ID | Microsoft Entra ID |  | • Security Requirements - Audit Logging • Compliance Requirements - SOC2 | 0 | 0 |  |  |  | infra
Data Integration | 11. Integrate Sync Services | 11.1 Open API Endpoint for Integrate Campaign Sync | • RESTful POST/PUT endpoint for Integrate to push campaign | MVP |  |  | 2.7 | • Core Requirements - Reporting & Analytics | 0 | 3 |  | S | 1 | Tanner to clarify joins
Data Integration | 11. Integrate Sync Services | 11.2 Campaign Result Push to Integrate | • Async/batch push of post-campaign performance and attribution data to Integrate. • Supports API (JSON) and webhook notifications for real-time updates. • Maps P360 attribution metrics to Integrate’s schema (e.g., impressions → Integrate_Campaign_ID) | Post-MVP | 11.1, 3.1 |  |  | • Core Requirements - Reporting & Analytics | 0 | 0 |  | S | 1 | Tanner to clarify joins
Tech Foundation | 12. Tech Foundation | 12.1 REDS Data Ingestion | • Hourly S3 file processing from TTD (REDS). • Validate/log corrupted files. • Performance target: Hourly processing for REDS. | MVP | AWS S3, TTD | AWS S3, TTD | 3.2 | • N/A | 0 | 0
Tech Foundation | 12. Tech Foundation | 12.5 External User Authentication | • Configure external identity providers (Auth0, Okta) per tenant, with OIDC-based federated login. • Support MFA/OTP fallback for Marketers and small orgs. • Map external users to P360 orgs with granular permissions (Buyer/Seller/Agency). | MVP | 4.1, 4.4, Auth0/Okta | Auth0/Okta |  | • Core Requirements - Integration Layer - Extensibility • Strategic Opportunity - Decoupling from Integrate's Tech | 0 | 0 |  |  |  | Infra
Tech Foundation | 12. Tech Foundation | 12.6 System Monitoring & Health Checks | • System monitoring and health checks – written on a feature-by-feature basis. Integration with monitoring and alerting systems. | MVP |  |  |  |  | 0 | 0 | Complex relationships with read/write and many to one |  |  | INfra
Tech Foundation | 12. Tech Foundation | 12.7 Sandbox/Test Mode | • Test mode where campaigns don't go live, bypassing sync to TTD. • Allows for safe testing and training. Environment management. Local, Staging, QA?, Prod | MVP | 4.1, TTD | TTD | 1.5, 2.4 |  | 0 | 0 | Complex relationships with read/write and many to one |  |  | Infra
Tech Foundation | 12. Tech Foundation | 12.8 Data Ingestion Monitoring (Basic version) | • Real-time dashboards and alerts for the status and health of all data ingestion pipelines (CSV, Bombora, REDS). • Includes metrics like record count, error rates, and processing latency. | MVP | 1.1, 1.3, 3.1, Bombora, 12.6 | Bombora |  |  | 0 | 0 | Complex relationships with read/write and many to one |  |  | redundant to datadog features | infra
Tech Foundation | 12. Tech Foundation | 12.9 Integration Health Dashboard (Basic version) | • Comprehensive view of API integration statuses (TTD, Salesforce), showing success rates, response times, and specific error logs for failed syncs or API calls. Alerts for sustained failures. | Post-MVP | 1.5, 2.4, 5.1, Salesforce, TTD | Salesforce, TTD, Bombora |  |  | 0 | 0 | Complex relationships with read/write and many to one | M | 2
Roles & Permissions | 13. Roles & Permissions | 13.5 Seller (External) | • Partner persona who manages listings and assets within the Marketplace. Cannot access buyer-side campaign or reporting features. • Can upload and manage seller-side assets • Can view marketplace performance of their assets • Can configure content syndication rules • Cannot access campaigns, programs, or buyer PII | Post-MVP | 12.1 |  | 12.1–12.4 |  | 0 | 0 |  | XL | 6
Roles & Permissions | 13. Roles & Permissions | 13.6 Agency (External) | • Agencies managing campaigns across multiple buyers. May have read-only or edit access across orgs based on permissions. • Assigned to multiple customer orgs • Read-only access to campaign setup and reports • Cannot access seller features • Cannot manage billing or org setup | Post-MVP | 4.6 |  |  |  | 0 | 0 |  | XL | 6
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Examples to demonstrate - need to align on T-Shirt to Eng Weeks mapping
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Excludes bombora integrations, as those are under data integration feature for S3/bucket Reply: This still has integrate integration, need to subtract 1 and add it to integration feature.
Note on N5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes we lean up scope.
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Is manual recon via UI or other means? Reply: @Nate Williams manual via UI
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed from bombora to capability of Audience Field Mapping Service and flagging bombora, etc as tables/dependencies.
Note on M14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Medium due to workflow.
Note on C21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sreenath Kurupath - shouldn’t this be a TTD data integration story to avoid redundancy?
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove UID2 from feature name, strictly identity for MVP.
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No bulk mvp
Note on D32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added program configuration for pre-sales
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I’m struggling with breaking apart salesforce as a separate sync apart from user functionality. If we do this for salesforce, we should do for all data sources but then we mix with a UI capability with this.
Note on D40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Early test results manually, fast.
Note on C52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Sreenath Kurupath - redundant to REDS story in data integration.

## Milestones
Milestone | Date | Description | Next Steps
1 | 2025-08-15 | Scope Alignment, Working Methods, Estimates/Commercials | BNTS - Deck from this week Sree - Excel from this week Greg - Tech Punchlist Tanner - Review features/use cases, provide feedback Tanner - Provide missing details (integration details, TTD clarifications from his call)
2 | 2025-08-15 | AI SDLC recommendations & specific tools | Anil to provide specific tool recommendations for AI driven SDLC
3 | 2025-08-15 | Metabase / reporting tools | Anil - provide alternative options
4 | 2025-08-22 | MSA + SOW | BNTS/P360
5 | 2025-08-22 | Technologies - Accounts, Access, etc (AWS, TradeDesk, Etc) | BNTS - Number of Seats
6 | 2025-08-22 | Tool accesses | Tanner - to provide licenses/test accounts etc.
7 | ASAP | Onboarding | Matthew Nalty
8 | 2025-08-15 | Confirm Datadog vs others? | Tanner to confirm
9 | 2025-09-01 | MVP Runway Backlog/Sprint Zero Kickoff | Access & 2 Sprints Defined
Formulas:
Date = +[Date, row above]

## Sheet4
Element | Description
Use Cases | Highlight specific, logical bundles where the product will be utilized to ensure a logical grouping of capabilities.
Features | Outline the key functionalities that will be developed to provide value and meet user expectations.
Description | Provide a concise overview of the capabilities, requirements, and how it fits into the overall product vision.
Release | Define the timeline and phases for launching the MVP to manage stakeholder expectations and planning.
Dependencies | Identify any interrelated tasks or systems required for successful MVP delivery to mitigate risks and facilitate smooth execution.
Integrations | Detail necessary connections with existing systems or third-party tools to ensure seamless operation and enhanced functionality.
Cross-Feature Impact | Assess how features interact with each other to maintain coherence and avoid conflicts within the MVP
P360 Requirements Reference | Ensure alignment with broader organizational requirements and standards for consistent and strategic development.
Screens | Describe the visual layouts and user interface elements to guide design and user experience considerations.
Tables | Specify the data structure and storage requirements essential for information handling within the product.
Questions/Complexity Drivers | Identify critical inquiries and potential challenges that could affect development to proactively address complexities.
T-Shirt | Use sizing estimates like "small," "medium," or "large" to quickly gauge the relative effort required for feature development.
Eng Weeks | Estimate the engineering effort needed in weeks to allocate resources and schedule effectively.
AI Feature Notes | Document considerations specific to AI functionalities to harness intelligent technologies throughout the MVP.
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Examples to demonstrate - need to align on T-Shirt to Eng Weeks mapping

## Xandr Gap Analysis
Capability | Xandr | P360 DSP | Delta/Opportunity | Recommendations
Audience Upload & Segmentation | Cookie matching, contextual targeting, RTSS for real-time data ingestion | CSV upload, Bombora mapping, UID2 sync to TTD | Strong parity; Missing: TTL & segment TTL versioning, real-time cookie ingestion | Add: Real-time cookie ingestion (Post-MVP), segment TTL management (MVP).
Forecasting | Real-time reach/impressions tied to inventory & bid data | Planned forecast engine (based on audience attributes) | Missing: inventory signals and TTD feedback loop. | Integrate TTD inventory API (Post-MVP) for dynamic forecasting.
Program & Campaign Setup | Multi-channel containers, advanced flighting, targeting rules | Basic hierarchy (Program > Campaign > Line Item) | Parity in structure; Missing: Cross-channel support, auto-inheritance rules. | Add: Auto-inheritance logic (MVP), multi-channel support (Post-MVP).
Line Item Execution | Granular bid control, PMP, video/CTV, exchange-level targeting | Basic display-only line items with pacing, bid config, and creative assignment | Missing: PMP, video/CTV, and exchange-level targeting logic | Prioritize: PMP support (Post-MVP), video/CTV formats (2026 roadmap).
Audience Activation | RTSS, deal-ID activation, real-time cookie match with exchange, multi-DSP export | TTD audience export with UID2 & Bombora enrichment | Functional parity for TTD; Missing: multi-DSP export flexibility for extensibility | Build: Extensible audience export framework (Post-MVP) for Trade Desk, Google DV360, etc.
Creative Management | Dynamic creatives, QA workflows | Marketers can upload assets; Sellers can list content in marketplace | No dynamic creatives or QA tools. | Add: Creative compliance classifier (AI-08) + dynamic creative templates (Post-MVP).
Attribution & Reporting | Real-time impression & click logs, multi-touch attribution, log-level access | Batch REDS files, Bombora matching, Metabase dashboards | Attribution is batch-based; Missing: multi-touch or event-level logs | Enhance: Real-time event streaming (Kafka) + multi-touch model (Post-MVP).
User Roles & Auth | Full RBAC, agency delegation, data masking | Buyer, Seller, Campaign Manager, Super Admin; Entra ID & Auth0 | Missing: no agency delegation, UI impersonation, or data masking by role | Add: Agency role (4.11) with delegated access (Post-MVP).
SSP/Exchange Access | Xandr Monetize + third-party SSPs | TTD-only for now | No exchange diversity; Missing: private marketplace (PMP) functionality (part of post-MVP) | Partner: Add 1-2 SSPs by 2026 for PMP deals.
Billing & Reconciliation | Native billing, fee breakdowns, exchange-level transparency | Salesforce reconciliation, manual bulk mapping | Misisng: auto-fee breakdowns, margin visibility, invoice matching | Automate: Fee breakdowns + invoice matching (Post-MVP).
Open API Access | Full external API for campaigns, creatives, segments, and reports | Internal APIs + "Integrate" sync only | Missing: public API catalog, limited partner extensibility (part of post-MVP) | Launch: Public API catalog (11.1) by 2026 for partners.
Marketplace | Xandr Curate (buyer-seller marketplace) | WIP: Seller Asset Management (12.1) with Seller Asset Management & Syndication | Aligned in vision; Missing: supply-side controls, monetization logic, deal flow (part of post-MVP) | Align with 12.3/12.4: Add syndication rules + seller performance dashboards (Post-MVP).

## Work Units (hidden)
Screens | 10
Tables/Int | 30
Note on C2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Less media marketplace.
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All tables, integrations w/ third parties, less media marketplace

## T-Shirt (hidden)
|  | BE | FS | DE
S | 1 | 4 | 3
M | 2
L | 4
XL | 6
XXL | 8
| 31 | 155 | 1240 | 60% | 30%
372
| BE | FE | DE
| 40% | 30% | 30% | 100%
| 4 | 4 | 3
| 496 | 372 | 372
| 3.1 | 2.325 | 3.1
|  | BE | 3
|  | FS | 2
|  | DE | 3